## Sheet1
Risk Matrices
| Negligible | Minor | Major | Hazardous | Catastrophic
Very Unlikely | Low | Low | Low medium | Medium | Medium
Unlikely | Low | Low Medium | Low medium | Medium | Medium HIgh
Moderate | Low | Low Medium | Medium | Medium High | Medium HIgh
Likely | Low | Low medium | Medium | Medium high | High
Very Likely | Low medium | Medium | Medium high | High | High
Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level
RSI | My wrists could be aching | Ensure I move wrists about | To keep my wrists safe for the future | Moderate | Minor
Computer Failure | Software/hardware failure on my desktop could prevent me from using it | Installed development software (Java, MySql, Eclipse, etc.) on laptop | Have a back up computer to continue working on from latest github commit | Unlikely | Hazardous
Long-term internet outage | Issues could arise with internet provider or the wider system preventing internet access | Depending on cause, could use mobile phone as a hotspot, otherwise prioritise issues which can be moved forward without internet access. | Minimize or avoid down-time due to loss of internet connection | Very Unlikely | Major
Personal/family emergency | Illness, injury or other crisis could occur and need to be dealt with as a priority | Notify QA as soon as possible with potential time frame for impact | Ensure stakeholders are notified of unavoidable delays as soon as possible so they have the opportunity to adjust their plans | Very Unlikely | Hazardous
Trainer/QA emergency | Illness, injury or other crisis could occur and need to be dealt with as a priority | Ensure I already have at least the majority of the information/support needed to complete the project | To be able to continue working independently until the external crisis is resolved | Very Unlikely | Minor
Long-term power outage | Power failure on a local or wider scale | If local, notify QA as soon as possible with potential time frame for impact, if wider, notify QA if possible. | Maintain communication where possible, focus on any opportunities to progress available | Very Unlikely | Hazardous
Global Pandemic | A virus could spread across the entire planet killing millions and infecting hundreds of millions | Get vaccinated | Just keep going, one way or another | Super Unlikely | Still working that out